## Slide 1: Migration plan for online delivery of math courses
By Amit Savkar

## Slide 2: Quick overview
Campus | Courses/class | Enrollment (Approximate)
Storrs | 137 | 6,109
Hartford | 18 | 465
Stamford | 20 | 525
Avery Point | 10 | 142
Waterbury | 11 | 216
Total | 196 | 7,454

## Slide 3: Big picture
Math 1060, Math 1070, Math 1071, Math 1131, Math 1132, Math 2110 and Math 2210 already have online instructional material.
The material will be copied for respective Husky CT sites to every course for the spring 2020 across all the five campuses.

## Slide 4: Student impact.
Course | Storrs | Stamford | Waterbury | Hartford | Avery Point | Total
Math 1060 | 124 | 34 | 26 | 60 | 14 | 258
Math 1070 | 442 | 101 | 37 | 35 | 11 | 626
Math 1071 | 379 | 149 | 44 | 103 | 26 | 701
Math 1131 | 417 | 66 | 31 | 67 | 26 | 607
Math 1132 | 943 | 83 | 34 | 74 | 25 | 1159
Math 2110 | 417 |  |  | 16 |  | 433
Math 2210 | 515 | 31 |  |  |  | 546
Total |  |  |  |  |  | 4,330

## Slide 5: Math 1020 and Math 1030
These course do not currently have any online instructional material available.
Resources will be provided for the instructors of these courses to create their material online.
Husky CT sites have already been created for these courses with instructors and students to have full access.

## Slide 6: Courses in Actuarial Science
The Infinite Actuary https://www.theinfiniteactuary.com/ will provide instructional material for Actuarial Courses that have exams.
They cover almost all the actuarial science topics.
Potentially willing to offer this service free or at a very reduced price.
Each professor would likely make use of this differently, however initially idea would be to assign the watching of certain videos, working certain problems and use discussion boards for student engagement.

## Slide 7: Courses with individual/non coordinated sections
We will go over the resources that are available to everyone one through the university IT and CETL.
There will be basic training on how to use Husky CT and webex.
Options for recording the videos will be provided.
Office hours that can be conducted over webex will be demonstrated during the meeting.

## Slide 8: Things to think about
Syllabus and changes to the syllabus.
Assessments in your course work.
Using online tools for possible assessments.
Think of Multiple-choice questions that can be used in Husky CT.
Re-distributing the grades if a final exam cannot be held in person.

## Slide 9: So far what has been done
You all have a Husky CT site.
For the courses that have online material, it will be copied to your course site in husky ct.
All faculty have an active Webex account.

## Slide 10: Asynchronous versus Synchronous
Keep
Keep the students at the center of all your thought process.
Describe
Describe whatever resources you are providing them with in a clear way.
Use
Use bulleted list instead of large paragraphs.
Provide
Provide them with step by step access to the material as much as you possibly can.

## Slide 11: Modes of communication
Expect that you will see an uptick in emails from your students.
Use the announcements feature in HuskyCT to communicate with your student directly.
You can use discussion boards to faciliatate conversations within your class asynchronously.
Discussion boards in HuskyCT
Using Piazza

## Slide 12: Where to look for resources.
CETL (Center for Excellence in Teaching and Learning)
https://ecampus.uconn.edu/keep-teaching
https://ecampus.uconn.edu/keep-teaching-get-started/
https://us-lti.bbcollab.com/collab/ui/session/playback
Taskforce in the department
  Amit Savkar, David McArdle, Myron Minn-Thu-Aye, Katie Hall, Anthony Rizzie.

## Slide 13: Departmental Minimum Expectations
Communicate often and as clearly as possible.
Online office hours (3 hours each week) in Webex or similar platforms.
Create content videos posted weekly.
  Live lectures held at the original class time or
  Pre-recorded content videos.
Appropriate assessments aligned with your original course syllabus.
  Virtual oral exams.
  Take home exams. (Time limited).
  Husky CT/WebAssign Quizzes.
  Submitting handwritten work in Husky CT.

## Slide 14: Syllabus and Assessments
Original grade break down must be honored.
Alternative form of assessments can be offered in place of previously planned assessments.

## Slide 15: Questions?

## Slide 16: Basic Tasks!
Creating a video:
  Kaltura
  Ipads
  Live webex.
  Lecture Hall Recording.

## Slide 17: Basic Idea
Using Webex. http://webex.uconn.edu
Demo.
  Login.
  Creating a meeting.
  Issues.

## Slide 18: Using HuskyCT
Making a folder
Uploading a file.
Attaching a video.

## Slide 19: Thank you!
Dave McArdle
Katie Hall
Anthony Rizzie
Myron Minn-Thu-Aye
All the instructors for sharing their online course content and helping clean up courses.
Keith Parks (IT)
David Des Armier (CETL)
Hengameh Vosough (IT-Husky CT)